|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **2021-2022** | **Key Players** | **APR 2021** | **MAY 2021** | **JUN 2021** | **JUL 2021** | **AUG 2021** | **SEP 2021** | **OCT 2021** | **NOV 2021** | **DEC 2021** | **JAN 2022** | **FEB 2022** | **MAR 2022** |
| **Key Events** | **AN** |   |   | AN Grand Council and Elections | Proposed AN/CAN Leadership Meeting |   | Possible Federal Election | Proposed AN/CAN Leadership Meeting  |  AN Grand Council Fall Assembly |   | Proposed AN/Leadership Meeting  |   | Proposed AN/CAN Leadership MeetingSigning CeremonyTake inventory on who’s in/outPI/IF Resourcing for Central Body |
| **Ratification Process** | **AN/FNs and Canada** | Ratification Comms Outreach | Ratification Comms Outreach | Ratification Comms Outreach | Ratification vote period-Concludes  | Parties meet to discuss vote results. |   Parties meet to discuss vote resultsRatification Comms Outreach |   Ratification Comms Outreach | Ratification Comms Outreach  | Ratification Comms Outreach  | Ratification Comms Outreach  | Ratification vote period-Concludes  | Parties meet to discuss vote results.Jointly announce vote result |
| **Pre-Effective Date activities** | **Pre-Implementation Support**  | **AN and Canada Later: Ratifying FNs** |   | Proposal Received.(Discussion/negotiation – PI/IF for Central Body) |   |  | Confirm Contribution Funding | Ongoing | Ongoing | Ongoing |  Ongoing |  Ongoing | Ongoing | AN pre implementation ready PI/IF submission to look at Central Body / AN support and request for assistance |
| **Enabling Legislation** | **AN/FNs and Canada** |  |  | Consultation (draft enabling legislation)  | Consultation (draft enabling legislation)  | Consultation concluded (draft enabling legislation)   |  Target to introduce Enabling Legislation – AN communications strategy/plan |  | Support Activities for Bill | Support Activities for Bill | Support Activities for Bill | Support Activities for Bill | Target Royal Assent |
| **Formalize Agreements** | **AN/FNs and Canada** |  Notice to FNs on proposed amendments to current funding agreements | Translated ANGA requires confirmation by AN., ANFA, IP to be translated by Canada  |   |   |   | Signing of ANGA Digitizing/HTML coding of ANGA + prepare to post online on the effective date. | Update ANFA | Update ANFA | Update ANFA | Update ANFA | Update ANFA |   |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | **2022-2023** | **Key Players** | **APR 2022** | **MAY 2022** | **JUN 2022** | **JUL 2022** | **AUG 2022** | **SEP 2022** | **OCT 2022** | **NOV 2022** | **DEC 2022** | **JAN 2023** | **FEB 2023** | **MAR 2023** |
| **Key Events** | **AN** | Future/Comprehensive Negotiations  |   | AN Grand Council |   |  Appointment of IOC representatives (Canada/FNs) |   |   | AN Grand Council Fall Assembly |  |  |  |   |
| **Ratification Process** | **AN/FNs and Canada** |  |  |  |  |  |  |  | Ratification Comms Outreach | Ratification Comms Outreach | Ratification Comms Outreach | Ratification vote period -Concludes  |  |
| **Pre-Effective Date Activities** | **Enabling Legislation** | **Canada****TAG &****Implementation Sector** |   |  Order In Council (OIC) setting effective date |   |   |   |   | Target Effective Date for ANGA and 1st fiscal transfer |   |   |   |   |   |
| **Formalize Agreements** | **AN/FNs and CIRNA/ISC** | Signing: ANFA, IP & amendments to current funding agreements |   |   |   |   |   |   |   |   |   |   |   |